Section 7

PERFORMANCE INDICATORS (PIs)

AND

PERFORMANCE MEASUREMENT SYSTEM (PMS)

# 1.0	Performance Monitoring

## 1.1	Introduction

This Appendix sets out the performance measurement process that will be applied to the works under this Contract.

## 1.2	Objectives

The objectives of the performance monitoring process are to ensure the Contractor.

- Delivers the works in accordance with the Specification and Preliminaries and commercial parameters; and

- Is incentivised to remedy non-performance in delivering the works.

Further, the measurement of works delivery will enable the Employer to:

- Understand through early indication of changing trends in performance such that good performance can be recognised and poor performance can be addressed:

- Provide relevant management information to the Employer with a view to providing tangible continuous improvement in the provision and performance of the works.

- To view feedback from occupiers/tenants/responsible person obtained by the Contractor and incorporated into the PI returns

## 1.3	Specification

### Rectification time for Defects – see below

| Response Times |  |  |  |
| --- | --- | --- | --- |
| Standard | Definition | Attendance Response time | Required Action/Response time |
| Priority one | Comprises a Health and Safety issue, | Attend the site the same day (during normal working hours) of receipt of the call from the Employer (Housing Investment team)/Contract Administrator. | Make safe any hazardous defects and as a minimum complete first fix within 30 minutes of attendance. If further actions required agree rectification time with CA |
| Priority two | An issue notified by the CA as urgent | Attend the dwelling within 24 hours (during normal working hours) of receipt of the call from the Employer (Housing Investment team)/Contract Administrator. | Resolve within 48 hours or agree differing time-frame with the CA. |
| Priority three | A superficial issue. | Attend the Site within 5 days of receipt of the call from the Employer (Housing Investment team)/Contract Administrator. | Resolve within 5 working days or agree differing time-frame with the CA. |

## Bedding-in Period

There will be a “bedding-in” period that allows the Contractor to make the transition from mobilisation to steady state operations. However, all PI’s must be measured and agreed from the commencement date. This will allow a period of adjustment for Works performance; the time allowable for bedding-in prior to the full application of performance measurement will be three (3) months from the commencement date.

Before the end of month three of the bedding-in period, the PI’s as set out in this document will be reviewed using the data collected during the first two months of operation and the PI’s amended and changed, if they are deemed inappropriate to achieve the goals as set out in the Objectives detailed above in clause 1.2. The month three PI review will focus on the volume of issues and whether the Performance Scores, taking account of the actual volumes are still achievable or reasonable (i.e. are the percentages set out in the current document too high or low taking into account the actual volume of transaction of the new contract), clarification as to meaning of the PI and how they should be measured, and adding additional criteria as deemed necessary.

# Performance Indicators (PIs) and Performance Reporting.

## 2.1	Objective

Performance Indicators (PIs) will be the performance measures against which the Contractor will be monitored in the provision of the works.

PI’s have been designed to provide objective and tangible measurement criteria that are aligned with the principal interests of the employer.

The PI’s are focused on outcomes and outputs that reflect significant areas of performance and the principal interests of the Employer. They are sufficiently challenging but not unobtainable and will apply to defined periods of time.

Performance data must be accurate and consistent and provide information that will be valuable to the employer to inform future business decisions.

## 2.2	Measurement

Both qualitative and quantitative mechanisms will be used to establish performance measurement.

9 PI’s have been developed for the Works as set out within this Appendix.  Each PI will be measured on a quarterly basis in accordance with the procedures set out hereafter.

The Employer is looking for continuous improvement throughout the life of the contract.  To measure this, prior to the anniversary of the commencement date, the PI set out in this document shall be reviewed and adjusted to demonstrate such improved performance.

By agreement a relaxation or exemption of the PI’s where special circumstances arise can be granted.  Any such requests by the Contractor must be made in writing and where feasible, requested prior to the event for which the relaxation or exemption is requested.

### Frequency

The Contractor and the Employer will undertake reviews of the Works to identify and to correct any poor performance in provisioning the Works as early as possible.

The Contractor shall formally audit its own performance against the PI on a quarterly basis and issue the results to the Employer.  The Employer will randomly audit an element of the Contractors PI measurement each month to ensure accurate reporting of performance. In the event that the Employer identifies inaccurate misreported audits, it will audit further elements of the PI to ensure the inaccuracy of the Contractors reporting is not consistent.  The cost of the additional sample audits in the event that further evidence of inaccurate reporting is found will be chargeable to the Contractor.

The outcomes of the PI measurement will be provided in an interim quarterly report (tabled five days prior to the monthly site meetings, please refer to PI 09) which will generate Corrective Action Notices (CAN’s) relating to individual PIs where the required levels of performance have not been achieved; the Contractor will be expected to deliver a Corrective Action Report (CAR’s) in response to a CAN, the format to be agreed prior to contract commencement and the frequency of reporting is to be no less than monthly.

Each quarter, the Employer is responsible for reporting the performance of the Contract to Southampton City Council (SCC).  A specific meeting will be set up on a quarterly basis to discuss and agree the report to be issued to the Council. The SCC quarterly reporting dates are:

22-Sept-17

15-Dec-17

22-Mar-18 23-June-18

### Format

The Contractor shall report the achieved PI performance outcomes as part of its monthly management report to the Employer, which is only submitted quarterly showing performance over the quarter utilising the pro-forma provided at Annex A below.

The quarterly scores ascertained for each of the PIs listed below will be entered into the tabled below to ascertain the PI % Achieved

| PI Ref | Element | Score Achieved | Weighting | Total |
| --- | --- | --- | --- | --- |
|  |  | Col A | Col B | Col A x Col B |
| PI 001 | Quality |  | 3 |  |
| PI 002 | Programme |  | 3 |  |
| PI 003 | Not used |  |  |  |
| PI 004 | H&S |  | 3 |  |
| PI 005 | Defects |  | 3 |  |
| PI 006 | Accounts |  | 2 |  |
| PI 007 | Complaints |  | 2 |  |
| PI 008 | Staff Retention |  | 2 |  |
| PI 009 | Report & Management Data |  | 2 |  |
| PI 010 | Communication with Residents |  | 3 |  |
| Total |  |  |  |  |
| Maximum Score |  |  |  | 115 |
| Percentage of maximum score achieved |  |  |  | % |

The Contract Administrator will utilise a quarterly performance report based on the “RAG” protocols on the following tolerance levels:

- Red  50% and below– serious concerns and need to escalate actions

- Amber  Between 50 and 70%– some concerns and need to focus on CANs to improve performance for the next measurement period; and

- Green 70% and above.

## Performance Indicators

The PIs for the provision of the Works are as follows:

|  |  |  | Source of | Calculation | Performance Scores |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PI Ref | Element | PI | PI | (quarterly |  |  |  |  |  |  |
|  |  |  | Measurement | data) | 0 | 1 | 2 | 3 | 4 | 5 |
|  |  |  | Data |  |  |  |  |  |  |  |
| PI 001 | Quality | Specification standards are achieved | CA requests for rectification works. | Requests/£10k value of work executed | Over 17 | 14-17 | 9-13 | 5-8 | 1-4 | 0% |
| PI 002 | Programme | Meeting time commitments | Site works programmes. | Sites on programme [or agreed extended programme]/Sites operating | Below 0.2 | 0.20-0.39 | 0.4 – 0.59 | 0.6-0.74 | 0.75 – 0.99 | 1 |
| PI 003 | Not used |  |  |  |  |  |  |  |  |  |
| PI 004 | H&S | No RIDDOR reportable incidents occur during month | Contractor / H&S reports | Number of RIDDOR reportable incidents | More than 1 RIDDOR reportable incident | 1 RIDDOR reportable incident | n/a | n/a | n/a | No RIDDOR reportable incident |
| PI 005 | Defects | The works are handed over with zero defects. | CA records defects on Practical Completion Certificate | Number of defects/ handovers. | More than 10 | 7-9 | 4-6 | 2-3 | 1 | Less than 1 |
| PI 006 | Accounts | Payment applications submitted by the Contractor are timely. | Comparison with agreed valuation dates | Days late | 4 or more | n/a | 3 | 2 | 1 | 0 |
| PI 007 | Complaints | The works do not inconvenience the neighbourhood whilst being executed. | Number of complaints received by the SCC | Number of substantiated complaints/ number of sites operating. | >4 | n/a | 2-4 | <2 | <1 | 0 |
| PI 008 | Retention of Staff (staff to be agreed) | The Contractor retains staff with experience of the estate and works to aid the works to keep on program. | Contractor staff records. | Number of staff leaving from Framework staff/size of required workforce. | Over 40% | 25 – 40% | 10 – 25% | 5 – 9.99% | 0.01 – 4.99% | 0 |
| PI 009 | Reports & Management Data | Monthly performance report and data are submitted at the appropriate time. | Transmittal date |  | Report not produced. | Report 0 to 2 days prior to the monthly performance meeting. |  | Report provided between 3 & 4 days prior to the monthly performance meeting. |  | Report provided 5 days prior to the monthly performance meeting. |
| PI 010 | Communication with Residents | Notification to Residents with relevant letters of planned works | Adverse feedback from Tenants to the Local Housing Office’s | Number of substantiated negative comments or complaints/ number of sites operating | >4 | n/a | 2-4 | <2 | <1 | 0 |

In addition to the information set out above the Contractor shall collect the following data:

- Waste to Landfill (appropriate details to be provided);

- Waste recycled (appropriate details to be provided);

- CO2 emissions reduction (initiatives)

- Apprenticeships schemes

- Use of local sub-contractors and suppliers

Quarterly Performance Report

Format

Balcony Works

This report is to be produced by the Contractor on a monthly basis.

| Performance Report | Quarter |  |  |  |
| --- | --- | --- | --- | --- |
| Overall Programme Status Highlight Report |  | Green |  |  |
| Notes: |  |  |  |  |
| Quarterly PI % achieved previous Quarterly PI % achieved |  | status | Green |  |
| Notes: |  |  |  |  |
| Corrective Action Notices from previous months awaiting Corrective Action Reports |  |  |  |  |
| Action: |  |  |  |  |
| CARs issued in Month |  |  |  |  |

| Overall Progress of Work |  | Position regards overall programme (as at reporting date) |  |  |  |  |  | % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sites not started on programme |  |  |  |  |  |  |  |  |
| Sites in progress |  |  |  |  |  |  |  |  |
| Sites completed |  |  |  |  |  |  |  |  |
| Sites handed over |  |  |  |  |  |  |  |  |
| Sites on hold |  |  |  |  |  |  |  |  |
|  |  |  |  | TOTAL |  |  |  |  |
|  |  |  |  |  |  |  | Green |  |
| Financial Control |  |  |  |  |  |  |  |  |
| Estimated Value of works executed in quarter |  |  |  |  |  |  |  |  |
| Payment Made Final Accounts cleared this Financial Year |  |  |  |  |  |  |  |  |
| Forecast Anticipated Final Accounts in Financial Year |  |  |  |  |  |  |  |  |
| Financial Status |  |  | Green |  |  |  |  |  |
| Major Risks & Issues |  |  |  |  |  |  |  |  |
| Major Risks |  |  |  |  |  |  |  |  |

| Major Issues |  |  |  |
| --- | --- | --- | --- |
| Major Risk & Issues Status |  | Green |  |

Monthly Data Sheets

Performance Measurement System

| PI 001 | Quality | >17 |  | 14-17 |  | 9-13 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 5-8 |  | 1-4 |  | 0 |  |
| PI 002 | Programme | <0.2 |  | 0.2 – 0.39 |  | 0.4 – 0.59 |  |
|  |  | 0.6 – 0.74 |  | 0.75 – 0.99 |  | 1 |  |
| PI 003 | Not used |  |  |  |  |  |  |
| PI 004 | H&S | More than 1 |  | 1 event |  | 0 events |  |
| PI 005 | Defects | More than 10 |  | 7-9 |  | 4-6 |  |
|  |  | 2-3 |  | 1 |  | 0 |  |
| PI 006 | Accounts | 4 or more |  | n/a |  | 3 |  |
|  |  | 2 |  | 1 |  | Less than 1 |  |
| PI 007 | Complaints | >4 |  | n/a |  | 2 - 4 |  |
|  |  | <2 |  | <1 |  | 0 |  |
| PI 008 | Staff Retention | >40% |  | 25 – 39% |  | 10 – 24% |  |
|  |  | 5 – 9% |  | 0.01-4% |  | 0 |  |
| PI 009 | Report and Management data | Not Produced |  | Only 2 days before |  | 5 – 9.99% |  |
|  |  | 3-4 days before% |  | 0% |  | Provided 5 days before |  |
| PI 010 | Communication with residents | >4 |  | n/a |  | 2 - 4 |  |
|  |  | <2 |  | <1 |  | 0 |  |

| PI Ref | Element | Score Achieved | Weighting | Total |
| --- | --- | --- | --- | --- |
|  |  | Col A | Col B | Col A x Col B |
| PI 001 | Quality |  | 3 |  |
| PI 002 | Programme |  | 3 |  |
| PI 003 | Not used |  |  |  |
| PI 004 | Health & Safety |  | 3 |  |
| PI 005 | Defects |  | 3 |  |
| PI 006 | Accounts |  | 2 |  |
| PI 007 | Complaints |  | 2 |  |
| PI 008 | staff Retention |  | 2 |  |
| PI 009 | Reports and Data |  | 2 |  |
| PI 010 | Communication with residents |  | 3 |  |
| Total |  |  |  |  |
| Maximum Score |  |  |  | 115 |
| Percentage of maximum score achieved |  |  |  | % |